## Sheet1
TARGET ECC - 1B
KPI Relationship | "BI Report KPIs (Phase 1c - ECC Sep 30)" | Customer Signoff on FSD | Owner | 85% | Remarks 10/11 | Customer Dependency | Revised Dev Status | 26% | 0% | 0%
|  | Status |  | DEV - ECC Completion |  | 2025-11-11 | 2025-11-11 | "Testing - SIT - ECC Completion" | "UAT - ECC Completion" | "PROD - ECC Completion"
Consumptions | Gross Billed Volume (Gross Consuption) | Submitted |  | Completed | "Further review required by DE team " |  |  | PENDING CUSTOMER FOR DATA
Consumptions, Reversals, Revisions | Billed Volume | Submitted |  | Completed | Ready for SIT |  |  | Inprogress
Consumptions, Reversals, Revisions | Reading Days | Submitted |  | Completed | Ready for SIT |  |  | PENDING CUSTOMER FOR DATA
Consumptions, Reversals, Revisions | Average Reading Days | Submitted |  | Completed | Ready for SIT |  |  | PENDING CUSTOMER FOR DATA
Consumptions, Reversals, Revisions | MLD | Submitted |  | Completed | Ready for SIT |  |  | PENDING CUSTOMER FOR DATA
Consumptions, Reversals, Revisions | Basic Revenue | Submitted |  | Completed | Ready for SIT |  |  | PENDING CUSTOMER FOR DATA
Consumptions, Reversals, Revisions | Envi Revenue | Submitted |  | Completed | Ready for SIT |  |  | PENDING CUSTOMER FOR DATA
Consumptions, Reversals, Revisions | Sewer Revenue | Submitted |  | Completed | Ready for SIT - untill Sep |  | Passed | Passed | Can we put in UAT? | Can we put in Prod?
Consumptions, Reversals, Revisions | SC Discount | Submitted |  | Completed | Ready for SIT - untill Sep |  | Passed | Passed | Can we put in UAT? | Can we put in Prod?
Consumptions, Reversals, Revisions | Revenue | Submitted |  | Completed | Ready for SIT |  |  | PENDING CUSTOMER FOR DATA
Consumptions, Reversals, Revisions | Water Tariff | Submitted |  | Completed | Ready for SIT |  |  | PENDING CUSTOMER FOR DATA
Consumptions, Reversals, Revisions | Average Tariff | Submitted |  | Completed | Ready for SIT |  |  | PENDING CUSTOMER FOR DATA
Consumptions, Reversals, Revisions | FCDA | Submitted |  | Completed | Ready for SIT |  |  | PENDING CUSTOMER FOR DATA
Consumptions, Reversals, Revisions | VAT | Submitted |  | In Progress | Dependent on revisions | " 10/11: ECC and S4 in same - dependency on map for GL accounts + (build of reversal vat table - Lawrance) Lawrance - (Revision + Reversal) Vat - revision flows " | Dev Pending - Lawrence | Not Started
Consumptions | Water Service Connections | Submitted |  | Completed | Ready for SIT |  | ? | PENDING CUSTOMER FOR DATA
Consumptions, Reversals, Revisions | Water Billing | Submitted |  | In Progress | Dependent on VAT |  | ? | Not Started
Installations | Meter Changes | Submitted |  | Completed | Ready for SIT | - Apr & Sep Pending Customer | Done | PENDING CUSTOMER FOR DATA
Reversals | Reversals: Count | Submitted |  | Completed | Ready for SIT | Jojo - CAN level - Sending email for data | ? | PENDING CUSTOMER FOR DATA
Reversals | Reversal: Billed Volume | Submitted |  | Completed | Ready for SIT |  | Passed | Passed | Can we put in UAT? | Can we put in Prod?
Reversals | Reversal: Basic Revenue | Submitted |  | Completed | Ready for SIT - may Failed | Jojo - CAN level - Sending email for data | ? | PENDING CUSTOMER FOR DATA
Reversals | Reversal: Envi Revenue | Submitted |  | Completed | Ready for SIT - may Failed | Jojo - CAN level - Sending email for data | ? | PENDING CUSTOMER FOR DATA
Reversals | Reversal: Sewer Revenue | Submitted |  | Completed | Ready for SIT - untill Sep |  | Passed | Passed | Can we put in UAT? | Can we put in Prod?
Reversals | Reversal: SC Discount | Submitted |  | Completed | Ready for SIT - untill Sep |  | Passed | Passed | Can we put in UAT? | Can we put in Prod?
Reversals | Reversal: FCDA | Submitted |  | Completed | Ready for SIT - may Failed | Jojo - Sending email for data | ? | PENDING CUSTOMER FOR DATA
Reversals | Reversal: VAT | Submitted |  | In Progress | Dependent on VAT | " 10/11: ECC and S4 in same - dependency on map for GL accounts + (build of reversal vat table - Lawrance) Lawrance - (Revision + Reversal) Vat - revision flows " | Dev Pending - Lawrence | Not Started
Revisions | Revisions: Count | Submitted |  | Completed | Passed | - | Passed | Passed | Can we put in UAT? | Can we put in Prod?
Revisions | Revision: Billed Volume | Submitted |  | Completed | Passed | - | Passed | Passed | Can we put in UAT? | Can we put in Prod?
Revisions | Revision: Basic Revenue | Submitted |  | Completed | Passed | - | Passed | Passed | Can we put in UAT? | Can we put in Prod?
Revisions | Revision: Envi Revenue | Submitted |  | Completed | Passed | - | Passed | Passed | Can we put in UAT? | Can we put in Prod?
Revisions | Revision: Sewer Revenue | Submitted |  | Completed | Passed | - | Passed | Passed | Can we put in UAT? | Can we put in Prod?
Revisions | Revision: SC Discount | Submitted |  | Completed | Passed | - | Passed | Passed | Can we put in UAT? | Can we put in Prod?
Revisions | Revision: FCDA | Submitted |  | Completed | Passed | - | Passed | Passed | Can we put in UAT? | Can we put in Prod?
Revisions | Revision: VAT | Submitted |  | In Progress | Ready for SIT | " 10/11: ECC and S4 in same - dependency on map for GL accounts + (build of reversal vat table - Lawrance) Lawrance - (Revision + Reversal) Vat - revision flows " | Dev Pending - Lawrence | Not Started
| Other/Misc Revenue Billing​ | Submitted |  | In Progress | Onhold | As per business - MWC | Not Started | Not Started
| Other/Msc Revenue​ | Submitted |  | In Progress | Onhold | As per business - MWC | Not Started | Not Started
Installations | Meter Ageing​ | Submitted |  | Completed | Ready for SIT | Jojo - Pending data from Leonard (EZ - D2 Team) MWC | Not Started | PENDING CUSTOMER FOR DATA
| Water Collection​ | Submitted |  | In Progress | Ongoing requirements analysis | 2019-12-01 | Not Started | Not Started
| Other/Msc Collection​ | Submitted |  | In Progress | Ongoing requirements analysis | 2019-12-01 | Not Started | Not Started
| ESG Report: Environment​ |  |  | In Progress | Ongoing requirements analysis | 2019-12-01 | Not Started | Not Started
| ESG Report: Environment​ |  |  | In Progress | Ongoing requirements analysis | 2019-12-01 | Not Started | Not Started
| ESG Report: Environment​ |  |  | In Progress | Ongoing requirements analysis | 2019-12-01 | Not Started | Not Started
| ESG Report: Social (Community)​ |  |  | In Progress | Ongoing requirements analysis | 2019-12-01 | Not Started | Not Started
| ESG Report: Social (Community)​ |  |  | In Progress | Ongoing requirements analysis | 2019-12-01 | Not Started | Not Started
| ESG Report: Social (Community)​ |  |  | In Progress | Ongoing requirements analysis | 2019-12-01 | Not Started | Not Started
Consumptions | WSC Bill Docs​ | Submitted |  | Completed | Ready for SIT | variance on all 8 BA - CAN Level from business - Roland | Failed | PENDING CUSTOMER FOR DATA
| Rate Code Changes​ | Submitted |  | Completed | Ready for SIT | Jojo - CAN level - Sending email for data | Done | PENDING CUSTOMER FOR DATA